## Demand
Project/Client Name | Resource Level | Resource Skill Set | Start Date | End Date | Hours Per Week
Harrington Manufacturing – NetSuite ERP Implementation | Senior Consultant | NetSuite - Record to Report | 04/01/2026 | 06/30/2026 | 40
Clearwater Retail – O2C Optimization | Consultant | NetSuite - Order to Cash | 03/20/2026 | 05/31/2026 | 40
Pinnacle Logistics – Supply Chain Rollout | Senior Consultant | NetSuite - Supply Chain | 03/21/2026 | 06/27/2026 | 30
Meridian Financial – R2R Consolidation | Manager | NetSuite - Record to Report | 05/01/2026 | 07/31/2026 | 30
Summit Healthcare – P2P Upgrade | Senior Consultant | NetSuite - Procure to Pay | 04/15/2026 | 07/15/2026 | 40
Vantage Distribution – Full Suite Implementation | Consultant | NetSuite - Record to Report | 04/01/2026 | 06/30/2026 | 30
Apex Pharma – NetSuite Assessment | Senior Manager | NetSuite - Supply Chain | 05/15/2026 | 08/31/2026 | 20
Internal – Pre-Sales Support | Analyst | NetSuite - Order to Cash | 03/21/2026 | 05/30/2026 | 20

## Employee Master
Employee Name | Level
Abdesattar Karim | Consultant
Benjamin Liu | Manager
Christine Chen | Manager
Crystal Brent | Senior Consultant
Delaney O'Neil | Senior Consultant
Ethan Osborne | Senior Consultant
Grace Schwieters | Analyst
Hannah Imhoff | Analyst
Jake Johnsen | Manager
Julie Loiben | Manager
Katharine Yu | Senior Consultant
Lance Falk | Analyst
Lexie Dutch | Senior Consultant
Marcy Minnerly | Manager
Mario DeFelice | Manager
Melissa Cross | Senior Consultant
Melissa Leighton | Manager
Neeraj Rajendran | Analyst
Nick Hernandez | Senior Consultant
Nick Kolbow | Senior Manager
Ryan Artz | Senior Consultant
Sammy Latif | Consultant
Shreyas Sampath | Manager
Tim Callesen | Senior Manager
Zareen Khan | Analyst

## Skills Master
Skill Set
NetSuite - Record to Report
NetSuite - Procure to Pay
NetSuite - Order to Cash
NetSuite - Supply Chain

## Resource Levels
Level
Analyst
Consultant
Senior Consultant
Manager
Senior Manager
Partner/MD

## Project Master
Project ID | Project Name
P001 | Accounting
P002 | Arevon
P003 | Assessment
P004 | Bank Integration
P005 | BlankStreet Advisory
P006 | ERP Evaluation
P007 | Evaluation
P008 | Flare
P009 | Grub WBS
P010 | L2C Assessment
P011 | NS Implementation
P012 | NetSuite Implementation
P013 | O2C Analyst
P014 | Operate
P015 | P2P
P016 | Phase 0
P017 | Phase 0 Design
P018 | Phase 1
P019 | Pigment Implementation
P020 | Procore Advisory
P021 | R2R
P022 | Secondment
P023 | Sui Foundation
P024 | SuiteBilling Implementation
P025 | SuiteProjects Advisory
P026 | Unassigned

## Supply
Employee Name | Level | Skill Set | Project Assigned | Week ending 3/21 | Week ending 3/28 | Week ending 4/4 | Week ending 4/11 | Week ending 4/18 | Week ending 4/25 | Week ending 5/2 | Week ending 5/9 | Week ending 5/16 | Week ending 5/23 | Week ending 5/30 | Week ending 6/6
Abdesattar Karim | Consultant | NetSuite - Record to Report | Phase 0 Design | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Abdesattar Karim | Consultant | NetSuite - Record to Report | P2P | 40 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Benjamin Liu | Manager | NetSuite - Procure to Pay | Accounting | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
Benjamin Liu | Manager | NetSuite - Procure to Pay | R2R | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Christine Chen | Manager | NetSuite - Order to Cash | NetSuite Implementation | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Crystal Brent | Senior Consultant | NetSuite - Supply Chain | NetSuite Implementation | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Delaney O'Neil | Senior Consultant | NetSuite - Procure to Pay | Unassigned | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Ethan Osborne | Senior Consultant | NetSuite - Record to Report | Phase 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Grace Schwieters | Analyst | NetSuite - Procure to Pay | Phase 1 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Grace Schwieters | Analyst | NetSuite - Procure to Pay | Phase 0 Design | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hannah Imhoff | Analyst | NetSuite - Order to Cash | NS Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hannah Imhoff | Analyst | NetSuite - Order to Cash | Bank Integration | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hannah Imhoff | Analyst | NetSuite - Order to Cash | O2C Analyst | 40 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Jake Johnsen | Manager | NetSuite - Supply Chain | Unassigned | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Julie Loiben | Manager | NetSuite - Procure to Pay | Flare | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Julie Loiben | Manager | NetSuite - Procure to Pay | Unassigned | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Katharine Yu | Senior Consultant | NetSuite - Record to Report | NetSuite Implementation | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Lance Falk | Analyst | NetSuite - Procure to Pay | Grub WBS | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Lexie Dutch | Senior Consultant | NetSuite - Order to Cash | Phase 0 Design | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lexie Dutch | Senior Consultant | NetSuite - Order to Cash | Phase 1 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
Marcy Minnerly | Manager | NetSuite - Supply Chain | Secondment | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Mario DeFelice | Manager | NetSuite - Procure to Pay | Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mario DeFelice | Manager | NetSuite - Procure to Pay | Unassigned | 16 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mario DeFelice | Manager | NetSuite - Procure to Pay | ERP Evaluation | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Melissa Cross | Senior Consultant | NetSuite - Record to Report | L2C Assessment | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Melissa Cross | Senior Consultant | NetSuite - Record to Report | Unassigned | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Melissa Cross | Senior Consultant | NetSuite - Record to Report | Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Melissa Leighton | Manager | NetSuite - Procure to Pay | Unassigned | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Neeraj Rajendran | Analyst | NetSuite - Order to Cash | Sui Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Neeraj Rajendran | Analyst | NetSuite - Order to Cash | Unassigned | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Nick Hernandez | Senior Consultant | NetSuite - Supply Chain | NS Implementation | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Nick Hernandez | Senior Consultant | NetSuite - Supply Chain | Phase 0 Design | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nick Kolbow | Senior Manager | Program Manager | Phase 0 Design | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 0
Ryan Artz | Senior Consultant | NetSuite - Record to Report | Arevon | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ryan Artz | Senior Consultant | NetSuite - Record to Report | BlankStreet Advisory | 20 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0
Ryan Artz | Senior Consultant | NetSuite - Record to Report | Procore Advisory | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ryan Artz | Senior Consultant | NetSuite - Record to Report | Operate | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Sammy Latif | Consultant | NetSuite - Procure to Pay | NetSuite Implementation | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Shreyas Sampath | Manager | NetSuite - Order to Cash | SuiteBilling Implementation | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shreyas Sampath | Manager | NetSuite - Order to Cash | SuiteProjects Advisory | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shreyas Sampath | Manager | NetSuite - Order to Cash | Pigment Implementation | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shreyas Sampath | Manager | NetSuite - Order to Cash | ERP Evaluation | 16 | 20 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0
Tim Callesen | Senior Manager | NetSuite - Supply Chain | NetSuite Implementation | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0
Zareen Khan | Analyst | NetSuite - Procure to Pay | Unassigned | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0